## Summary
(This page under construction)

## BRD 1
Project: eVal | [5 empty] | Testing Status/Results
Area of Functionality being tested: Various enhancements as described in BRD 1 | [5 empty] | # of Cases:
Tester: Anne | [5 empty] | # Tested:
Developer: Anne | [5 empty] | # Pass:
Business validation by: Donna | [5 empty] | # Fail:
Technical Team: WA State eVal | [5 empty] | Success Rate:
Date:
Test Status (Open/Closed): Open
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Test data | Expected Result | Actual Result - 2/24/15 Walkthrough with Anne using Seattle sandbox | Actual Result - 3/2/15 Donna hands-on testing with Seattle sandbox | Actual Result - 3/3/15 Donna testing fixes in Seattle sandbox | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
1 | 1.1 | 1.1T | Disable the user-generated and system-generated messages |  | Messages are disabled either through a District configuration setting administered by the DA role, or pre-set for Seattle by the eVal team |  | There is no longer the current functionality for the Seattle user by which a user, or the system, can send a message. This should include all buttons, UI screens and alerts related to these messages are either gone completely or disabled. | Messaging is no longer visible to the user. This is a Seattle-wide setting configured by the eVal team. | Messaging is no longer visible to the user. This is a Seattle-wide setting configured by the eVal team. | n/a | 2 | 2015-03-02 | P
1 | 1.2 | 1.2T | Ability for eVal to run on Firefox | Firefox is loaded on the test machine | Open Firefox. Log into EDS and then open eVal. Once in eVal, act as both a teacher and an evaluator and walk through all functionality related to goal setting, observations, summary scores and reporting. | (If we can validate that there are pilot participants actively using Firefox, then we can skip this test scenario and record that we are comfortable based on Pilot experience) | There are no issues related to the browser. | At this point, we have had many pilot users (both evaluators and teachers) running on Firefox. eVal team has received and resolved 1 issue. We can consider this requirement as fulfilled. | n/a | n/a | n/a |  | P
1 | 1.3 | 1.3T | The ‘Allow this School to Perform Principal Assignment’ checkbox option on the eVal Assignment tab should auto-default to being checked across all SPS schools | User is logged in as DA. | Go to Set Up screen. The checkbox that allows a principal to self-assign should be checked. Then log in as a school administrator and confirm that you can do assignments. |  |  |  | Is this change only in Prod? I don't see it in Seattle Sandbox when I switch schools | n/a | 1 | 2015-03-02 |  |  |  | Yes, only on production.
1 | 1.4 | 1.4T | Removal of any functionality that assumes the start or end time of an observation. Our solution is to hide the start and end times from Seattle users and only display the date. For informal observations, the date will be auto-stamped the current date. Though the eVal system itself also stores a time (because it is a date/time stamp), when this field is displayed to the user, it will only show the date. | User is logged in as an evaluator. | Go to Observation panel and click to begin a formal observation. s. |  | Whether or not you use the calendar functionality, the tool should not provide a default begin time or end time. Click in the begin time field and end time field to make sure nothing auto-populate | Using either impromptu or formal, the date/time comes up blank and user has a button now called "Change Date" but Anne can re-name it to "Set Date" | The latest UI changes successfully address the issue. The only remaining item is that when the teacher looks at observation settings, the end time is still displaying. | Fixed | 3 | 2015-03-02 | P |  |  | Fixed.
1 | 1.5 | 1.5T | All references to “Self Assessment” should read “Self Assessment” and should not be shortened to “Assessment” | User is logged in as a Teacher. | Review all parts of the Self Assessment panel and the Scoring panel. Confirm that if Self Assesment is referenced, it is not shortened to "Assessment." Log in as an evaluator and repeat above. |  | Confirm that if Self Assesment is referenced, it is not shortened to "Assessment." | Per Anne, she went thru UI and made the updates (I don't remember where they were so will take her word) | Labels are correct when logging in as teacher. We need to wait until new evaluation workflow to validate changes as evaluator (because self-assessment won't be part of Summary panel anymore) | n/a | 1
1 | 1.6 | 1.6T | Observations should have persistent, consistent names | First log in as evaluator, then as teacher. | Create multiple observations, one after another. Review how these are named. Review how these are represented on the Observation report. Review how these appear in the dashboard and on the Observation panel. Go to Summary panel (report in draft mode) and see how observations appear in Report settings. Include the observations in the report. Review the report. Then, when logged in as teacher, review same. |  | Observations should each have a unique name including school year and a sequential number. (If a teacher has some observations done by a different evaluator, then that teacher's evaluators will see a skip in sequence numbers -- that is OK) | Anne will reduce the amount of text that appears in the tool tip so it reads "2014-2015.1" and then only shows name, date and location if populated. No field labels; separate by semi-colon if data available. | Working as expected. Can we also add this identifier into the default observation title instead of using the date that the observation was created? | Fixed | 1 | 2015-03-02 | P |  |  | Fixed
1 | 1.7 | 1.7T | The Assignment screen will be able to display infinite number of evaluators for any school. | Log in as School Administrator at a school that has over three evaluators assigned to it. | Look at the Assignment screen (part of Set-up). |  | All evaluators assigned to that school should be available for assignement to any teacher in that school. |  | Working as expected. | n/a | 1 | 2015-03-02 | P
1 | 1.8 | 1.8T | The evaluators will have a generic container into which they can upload artifacts that are not related to a specific observation. | Log in as evaluator | Upload an artifact but do not relate it to a specfic observation |  | Functionality exists. | Completed. Anne needs to update so that it can be made not visible to the teacher. But will be purged at end of year -- so evaluator must downlaod if they want to keep them. | Uploading the artifact works fine, and it links correctly to framework, and we no longer have reflections text. However, it appears the visibilty settings are reversed. When the evaluator unchecks the Visible box, then the evaluator no longer sees it, but the teacher still sees it. | Fixed | 1 | 2015-03-02 | P |  |  | Fixed.
1 | 1.9 | 1.9T | Artificats should have unique identifier and that identifier should be used in any screens by which the user is trying to locate their artifacts |  | (Complete once this item has been prioritized)
1 | 1.1 | 1.10T | When uploading an artifact, the button should say “Save”, not “Insert” |  | (Complete once this item has been prioritized)

## BRD 2
Project: eVal | [5 empty] | Testing Status/Results
Area of Functionality being tested: Scoring | [5 empty] | # of Cases:
Tester: Anne | [5 empty] | # Tested:
Developer: Anne | [5 empty] | # Pass:
Business validation by: Donna | [5 empty] | # Fail:
Technical Team: WA State eVal | [5 empty] | Success Rate:
Date:
Test Status (Open/Closed): Open | [5 empty] | (Note: Refer to print screens of BRD2 thru-out testing)
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Test data | Expected Result | Actual Result - 2/24/15 Walkthrough with Anne using Seattle sandbox | Actual Result - 3/2/15 Donna hands-on using Seattle sandbox | Actual Result - 3/3/15 Donna testing fixes in Seattle sandbox | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
2 | 2.1 | 2.1T | Related to the observation process, remove inference of rating at the component level, domain level or overall observation level. This applies for all places in the current UI where now the user would be able to provide a score as part of the observation process (i.e., any checkbox that would allow the user to denote an actual score should be removed; any area where it looks like one “should have” entered a score at component or observation level should be removed). These changes should apply equally to the teacher and the evaluator online experience. | Log in as evaluator and find a teacher's record which has a completed observation. | Review all UI panels related to that observation. Review the print screens included in BRD 2. Confirm that all inferences as described in the requirement description have been removed. Logout and login as a Teacher. Repeat above. | Seattle Sandbox test data | There is no inference that one can score at component or observation level; resulting UI remains readable and has not inadvertently become confusing due to the changes. | Appears completed. | Appears completed. |  | 1 | 2015-03-02 | P
2 | 2.2 | 2.2T | Observation reports should not contain any inference that scoring at the domain, component or overall observation level is possible. Report settings should not include option to include any observation scores. | Same as above | Same as above but for the Observation Report | Seattle Sandbox test data | Same as above | Appears completed. | When Rubrics is selected, the framework appears in the report along with the headings "Unsat", "Basic", etc. Though this is acceptable in the Observation panel when selecting a claim statement, we do not need the full rubric ever appearing in either the observation or evaluation report, plus, by doing so, it infers a score in the report. Instead, we should have the ability for claim statements and supporting evidence to appear in the report, but not the rubric inself. |  | 1 | 2015-03-02 | F
2 | 2.3 | 2.3T | When a user selects “Highlight and add to evidence”, they should immediately receive a prompt to enter the evidence that supports this claim statement, and the text box for entering that evidence should be opened and accessible to them. | Log into eVal as an evaluator. | Using an existing (unlocked) observation, or creating a new one, go to the Observation panel and view instructional rubrics. Highlight a claim statement and click with right mouse key. Choose "Hightlight and add to evidence." |  | User should receive prompt to enter evidence supporting claim statement and then be directed to the section in the UI where this information can be entered. (The user is not "forced" to enter the data should they decide not to.) | Appears completed. | Working as expected; however, when the teacher adds a claim statement, there is an extra line space between the claim statement and the evidence supporting it. There is no extra line space for the evaluator's input betweeen the claim statement and the evidence and that makes it easier to read and see the context across the two items. Can we remove the space occuring for the teacher? |  | 1 | 2015-03-02 | P |  |  | Good catch. This is only in FF. Found report on Telerik (vendor that supplies the editor we use). http://www.telerik.com/forums/rad-editor-adds-line-break-to-empty-content-in-firefox. I have removed the <br> when I see it when loading the editor. I haven't been able to reproduce the space between the CLAIMS STATEMENT and the EVIDENCE though.
2 | 2.4 | 2.4T | Need to ensure that a user selection of claim statements would not visibly be associated with a rating or score for any observation either within the UI or on any printed report | Log into eVal as an evaluator. | Using an existing (unlocked) observation, or creating a new one, go to the Observation panel and view instructional rubrics. Highlight a claim statement and click with right mouse key. Choose "Hightlight and add to evidence." Then go to the Scoring panel for that teacher and look at their summative evaluation report. |  | The claim statement should appear but without any inference to an actual score. | [5 empty] | P
2 | 2.5 | 2.5T | Related to summative evaluation scoring: Remove inference of rating at the component level anywhere in the UI where, currently, the user would be able to provide a score at the component level (i.e., any checkbox that would allow the user to denote an actual score at the component level should be removed) | Using new workflow for evaluation report, select a teacher who has had multiple observations and for whom summative scores have been entered | Look at the scoring panel. |  | The only scores that should appear should be at the domain level (except for Student Growth which are scored and which are, in fact, components of State Criteria). Other than described above, there should be no inference that observations could be scored or that other components could be scored (i.e., nothing in the UI should indicate that the user could score at that level). | Appears completed. | Appears completed, except that the tooltip that pops up when you hover over an observation in the panel references an observation score. Please remove this info from the tool tip. |  | 1 | 2015-03-02 | P |  |  | Fixed
2 | 2.6 | 2.6T | Evaluation reports should not contain any inference that scoring at the component level is possible. Report settings should not include option to include component scores. | Using new workflow for evaluation report, select a teacher who has had multiple observations and for whom summative scores have been entered | Look at report printed to screen. Then move report from draft to Waiting for Teacher's Acknowledgement so that a PDF is created. Look at the PDF |  | The only scores that should appear should be at the domain level (except for Student Growth which are scored and which are, in fact, components of State Criteria). Other than described above, there should be no inference that observations could be scored or that other components could be scored | Appears completed. | Appears completed. |  | 1 | 2015-03-02 | P
2 | 2.7 | 2.7T | Disable any scoring ability for Non- Student Growth components when entering evaluation scores | Using new workflow for evaluation report, select a teacher who has not yet been scored. | Expand the State Criteria which have Student Growth components. Then expand a State Criteria that does not have Student Growth component. |  | The user can enter a score for the Student Growth component but cannot enter any other scores at component level, neither non-SG components that roll up with SG components, or other components. | Appears completed. |  |  | 1 | 2015-03-02 | P
2 | 2.8 | 2.8T | Highlight on the UI where the evaluators should go to rate Student Growth components | Using new workflow for evaluation report, select a teacher who has not yet been scored. | Look at the scoring panel. |  | It should be quickly obvious to the user where to click to expand panels and locate Student Growth components. (Note - this is a nice-to-have; not a requirement)
2

## BRD 3
Project: eVal | [5 empty] | Testing Status/Results
Area of Functionality being tested: Reports | [5 empty] | # of Cases:
Tester: Anne | [5 empty] | # Tested:
Developer: Anne | [5 empty] | # Pass:
Business validation by: Donna | [5 empty] | # Fail:
Technical Team: WA State eVal | [5 empty] | Success Rate:
Date:
Test Status (Open/Closed): Open | [5 empty] | (Note: Refer to print screens of BRD2 thru-out testing)
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Test data | Expected Result | Actual Result - 2/24/15 Walkthrough with Anne using Seattle sandbox | Actual Result - 3/2/15 Donna hands-on in Seattle sandbox | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
3 | 3.1 | 3.1T | Hide "Score Alignment Report" | (Was this necessary after all? Or was it only available to DA?) | Logged in as teacher and looked at Self Assessment panel |  | Report is no longer listed | Appears completed. | Appears completed. | 1 | 2015-03-02 | P
3 | 3.2 | 3.2T | Observation reports and Evaluation reports should not make any reference to a data entry field if a value for that field is not provided by the user, nor to a reporting section if that section was not selected for the report. Specifically, the report should not say “No information provided” for a missing field, nor say “Session Recommendations: No responses found” if the user has not chosen to include Session Recommendation, nor say “Post-Conference Prompts” if there are none to be found, etc. | Select a teacher with multiple observations whose report is still in draft form. | Go through that teacher's observations and update the data so that for each kind of data that could be entered, nothing is entered (i.e., no responses to prompts, no recommendation responses, etc.) On the scoring panel, leave Reflections, Final Notes and Final Recommendations blank. Under Report Settings. Print the report to screen. Then move the report to "Waiting for Teacher Ack" and open the PDF file. |  | There should be no indicators telling the reader that information is missing. Specifically, if a user choose not to enter a prompt response, then there should be no reference to that prompt at all. If a user choose not to enter Final Recommendations, then there should be no inference to that section. | Appears completed -- but Donna should runs some more tests in Seattle sandbox. | Appears completed. | 1 | 2015-03-02 | P
3 | 3.3 | 3.3T | [Related to settings for the Observation report -- need to clarify with Anne]
3 | 3.4 | 3.4T | Wherever the pencil and scissors icons currently appear throughout the Observation UI or Observation report, they should be replaced with descriptive text. |  | On Observe/Score panel, use the Notes Editor to enter and tag comments. Now change the view to Rubric view, highlight a claim statement and using right mouse key select "Highlight and add to evidence." Next, look below the rubric for where the comments and the highlighted text appear. Next, look at the observation report. |  | The comments entered into Notes Editor should not have a scissors; the claim statement should not have a highlight. Instead, comments will have no heading or extra identifier. Claim statements will have header of "Claim Statement" | Appears complete. | Appears complete. | 1 | 2015-03-02 | P
3 | 3.5 | 3.5T | The Evaluation report should have a default print setting selected District-wide by the District. (The solution for this requirement will be that a new report will always default to having no settings set, plus, we have made several data elements that used to be optional now be required, required so that they are no longer print settings. Bascially, the user must choose which observations to include. See slide deck for details.) | Log in as evaluator and select a teacher with multiple observations and whose report is in Draft. | On the Scoring panel, expand Reporting settings. Choose an observation to include. Preview report and confirm the observation is there. Move the report to Ready for Teacher Conference. Go back to scoring panel and try to change the options. Then move the report back to Draft and try again. |  | Report setings should default to nothing checked. Then once settings are selected (when Report is in draft mode), and report is moved out of draft mode, settings should be locked. But if report is moved back to Draft, then settings should be configurable again. |  | Not sure this is completed in Seattle sandbox -- should wait until new workflow so we can see this all together
3 | 3.6 | 3.6T | The pencil and scissors icons should be removed from the Evaluation report and replaced with descriptive text. |  | Follow steps for 3.4T. Next, go to the Scoring panel for Summative scores and include that observation in the report settings (must be in Draft mode). Move report into "Ready for Teacher Ack" and look at PDF file. |  | The comments entered into Notes Editor should not have a scissors; the claim statement should not have a highlight. Instead, comments will have no heading or extra identifier. Claim statements will have header of "Claim Statement" |  | Appears complete | 1 | 2015-03-02 | P
3 | 3.7 | 3.7T | List the Observation # in Report Settings (right now the observations are only indicated by date which is not an easy identifier for the user to know which observation is which) |  |  |  |  | Completed -- see suggested changes on related test case BRD 1 | Appears complete | 1 | 2015-03-02 | P
3 | 3.8 | 3.8T | When the teacher prints the Observation Report, it should be titled “Observation Information” so that it is clear that this is not the same as the formal Observation Report that is provided to the teacher by the evaluator. |  |  |  |  | See more detailed requirements in modified CR.
3 | 3.9 | 3.9T | All users need ability to download any or all data in PDF form

## BRD 4
Project: eVal | [5 empty] | Testing Status/Results
Area of Functionality being tested: PDF Creation | [5 empty] | # of Cases:
Tester: Anne | [5 empty] | # Tested:
Developer: Anne | [5 empty] | # Pass:
Business validation by: Donna | [5 empty] | # Fail:
Technical Team: WA State eVal | [5 empty] | Success Rate:
Date:
Test Status (Open/Closed): Open | [5 empty] | (Note: Refer to print screens of BRD2 thru-out testing)
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Test data | Expected Result | Actual Result | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
4 | 4.1 | 4.1t | Automated process for transferring PDF files to District -- Test case will wait until District has procured document management software; creation of this delivery mechanism will be done in colloboration across eVal team, District and software vendor
4 | 4.2 | 4.2T | PDF files are named or flagged within eVal in such a manner that they can automatically be recognized by the District’s system for appropriate indexing. (Until document management software is in place -- see 4.1T above -- this requirement is limited to the ability for unique and understandable naming convention for the PDF files) | Report is in Submitted state. | User downloads PDF through eVal front-end and, through the back-end, eVal team provides access to testing team of the actual PDF file. |  | PDF naming convention is as follows: FILE NAME = [cert #] + "_" + DateTime + "_" + [n] where n is the version number (for most files, n will be "1" as there will only be one PDF created that year for that teacher; in rare instances, a submitted report will be moved back to Draft. In this case, n will be "2")

## BRD 6
Project: eVal | [5 empty] | Testing Status/Results
Area of Functionality being tested: Seattle's download file | [5 empty] | # of Cases:
Tester: Anne | [5 empty] | # Tested:
Developer: Anne | [5 empty] | # Pass:
Business validation by: Donna | [5 empty] | # Fail:
Technical Team: WA State eVal | [5 empty] | Success Rate:
Date:
Test Status (Open/Closed): Open | [5 empty] | (Note: Refer to print screens of BRD2 thru-out testing)
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Test data | Expected Result | Actual Result Donna using Seattle sandbox on 3/2/15 | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
6 | 6.1 | 6.1T | Data file to be made available for download to District Administrator via the Reporting screen within eVal | Log in as DA | On the Reporting tab, click on "Seattle Custom Report" and select downlaoding the data as Excel. Then, select downloadin the data as tab delineated. | Both Seattle sandbox and, ultimately, Pilot data out of production | User receives a file with the data elements listed in the Specification created for this BRD. | Cannot test until new workflow is moved to Seattle sandbox.
6 | 6.2 | 6.2T | The file should contain one single record for each teacher | Download file per 6.1T above | Review data. |  | File should contain one record per teacher per school year.
6 | 6.3 | 6.3T | Data to be available for download at any time | Download file per 6.1T above | Review data. |  | The data should include all teachers currently in the eVal system, regardless of whether their evaluation is completed or not
6 | 6.4 | 6.4T | The name of the download report that appers on the eVal UI when a user goes to retrieve the data should be “Custom Seattle Download Report”
6 | 6.5 | 6.5T | The file name of the downloaded file must be uniquely identifiable from other files downloaded through this process

## BRD 8A
Project: eVal
Area of Functionality being tested: Seattle's download file
Tester: Anne
Developer: Anne
Business validation by: Donna
Technical Team: WA State eVal
Date:
Test Status (Open/Closed): Open
BRD | Req ID | Test ID | Objective | Pre-condition | Steps | Expected Result | Actual Result Donna using Seattle sandbox on 3/10/15 | Iteration (1, 2, etc.) | Date last tested | Status (P/F) | Defect ID | Tester Notes | Dev Notes
8A | 8A.1 | 8A.1T | New panel through which user can clearly see status of evaluation report through each lifecycle phase |  |  |  | See notes about useability; Can we remove the gray and leave the panels white? | 1 | 2015-03-10 |  |  |  | Done
8A | 8A.2 | 8A.2T | Appropriate controls are in place so that evaluator must choose an over-ride if they wish to score the report without student growth scores, including ability to enter explanation. |  |  | If over-ride is selected, the user will not receive error messages regarding student growth scores missing | SG and overall score is not always generating and sometimes say "INC", with an error message printed on the report, when SG scores are skipped, even with over-ride. Also, if some scores are entered but not all, we should not include any of those scores in the overal scoring. | 1 | 2015-03-10 | F |  |  | Entered as bug. In progress.
8A | 8A.3 | 8A.3T | Appropriate controls are in place so that evaluator must choose an over-ride if they wish to submit the report with the teacher’s electronic acknowledgement, including ability to enter explanation. |  |  |  | Works as expected | 1 | 2015-03-10 | P
8A | 8A.4 | 8A.4T | Appropriate controls are in place so that evaluator must choose an over-ride if they wish to complete the process using paper, including ability to enter explanation. |  |  |  | Works as expected, but can we call it "Evaluator Over-rides" instead of "Evaluation" and "Explanation" instead of "Comment"? | 1 | 2015-03-10 |  |  |  | Done
8A | 8A.5 | 8A.5T | If the report has not yet been submitted, the evaluator can move it back to previous phases, including back to Draft |  |  |  | Works as expected | 1 | 2015-03-10 | P
8A | 8A.6 | 8A.6T | Once submitted, evaluators need District Administrator assistance to move it back to Draft. |  |  |  | Let's wait and test this later | 1
8A | 8A.7 | 8A.7T | The report’s status is changed to Submitted as soon as the teacher opens the report and receives the “You are now receiving your report” pop-up box |  |  |  | The pop-up box is not yet working -- see notes for error message print screen. Perhaps instead, let's have the teacher click on a button that says "Receive Report" (instead of the PDF incon) and then they get the pop-up box and then it prints to screen. They can print PDF if they want to. | 1 | 2015-03-10 | F |  |  | Fixed. Due to missing file.
8A | 8A.8 | 8A.8T | The ability to set report settings will be adjusted so that the report settings are per specific evaluation report and are considered part of the creation of the report. The settings can only be modified when the report is in Draft. |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.9 | 8A.9T | The State Criteria, including Student Growth scores, are the only rubric available on the report |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.10 | 8A.10T | There is no longer a distinguish made between “completed” and “uncompleted” observations |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.11 | 8A.11T | Final Evaluation Sections (Reflections, Final Notes, Final Recommendations) are no longer options on the report settings, as they are included as default settings. |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.12 | 8A.12T | Report settings should default to not selected. |  |  |  | Working as expected. But any chance we can default the report settings panel to always be open since it's hard to find and when it's closed there is no indication to the user that it is hiding there? | 1 | 2015-03-10 | P |  |  | Done
8A | 8A.13 | 8A.13T | The report should be titled “Seattle Public Schools Certified Teacher Summative Evaluation Form” and include the following information: Teacher; Evaluator; School year; Current year’s evaluation cycle info and next year’s evaluation cycle info; Report status ; Audit fields ; Final Evaluation Sections (Reflections, Final Notes, Final Recommendations); |  |  |  | See mock-up which Donna will get to you ASAP today | 1 | 2015-03-10 | F
8A | 8A.14 | 8A.14T | The report created through this new workflow should either (1) only be available via the Summary panel or (2) if it is included in the Reports panel, it should be named in such a way that the user understands they are about to print the summative evaluation report just as they would if they were printing from the Scoring panel. |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.15 | 8A.15T | The teacher will have a status screen letting them know what action to take on their report. |  |  |  | Working as expected. Can we change column heading from "Final Report" to just "Report"? | 1 | 2015-03-10 |  |  |  | Done
8A | 8A.16 | 8A.16T | The current navigation dashboard that evaluators use to see all scores and select a teacher for further scoring will be replaced by a new navigation dashboard which includes report status |  |  |  | I think it's working -- but can you check out my notes regarding those that say "Received"? | 1 | 2015-03-10 |  |  |  | The report should never show in state "RECEIVED", although behind the scenes there is one so that we can track when it was received vs the case when the pr doesn't require receipt. Not sure how it got in that state on seattle site. I will check to make sure there isn't a condition where it is getting stuck in that state (possible error occurred).
8A | 8A.17 | 8A.17T | New dashboard will be available to all roles except teacher showing work-in-progress summary for lifecycle phases |  |  |  | [not yet developed -- wait until the new workflow is in place for teachers/evaluators] | 1
8A | 8A.18 | 8A.18T | The Visibility Settings panel will be removed. |  |  |  | Working as expected | 1 | 2015-03-10 | P
8A | 8A.19 | 8A.19T | Here is the blurb to be placed above the report settings panel (see req for full blurb) |  |  |  | Working as expected. But can we add one more blurb for when it has been submitted so that instead of saying "Move back to draft for changes" it says "“This report has been submitted. Report settings are locked and cannot be changed.” | 1 | 2015-03-10 |  |  |  | Done
8A | 8A.20 | 8A.20T | Blurb to appear above Preview button |  |  |  | Working as expected | 1 | 2015-03-10 | p
8A | 8A.21 | 8A.21T | SIGNATURE BLOCK:; ; Signature block ONLY to be printed when (1) user creates a PDF file AND (2) user has selected “Drop to Paper”. ; ; Signature block to not print to screen.; ; Signature block to not print on PDF in any other circumstances. |  |  |  | [not yet tested by Donna] | 1 |  | P
;