## Sheet1
# | Item | Phase | Priority | Type | Maturity | Details as of April 22
1 | Change extract file name | Release 2 | High | Fix | Approved | Donna and Anne to finalize
2 | Ability to keep artifacts year after year - step 1 (don't purge) | Release 2 | High | New | Approved | For now, we just want to exclude the artifacts deletion from the yearly purge
3 | Ability to keep artifacts year after year - step 2 -- need UI that allows user to see artifacts across years | Release 3 |  |  |  | (This is functionality within eVal; not the standalone evidence manager we spoke of)
4 | Ability to select artifacts to print w/ Summative Eval report | Release 2 | Med | New | Concept | Depends on complexity; otherwise will deal with manually this Spring
5 | Add "Teacher Response" to Summative Workflow | Release 2 | High | New | Contract requirement | We could live without this for the Spring, but we must have solution for next year
6 | Add "Teacher Response" to Observation report process | Release 3
7 | Look at new UI approach for linking notes from notes editor to claim statements | Release 3 | High | New | Concept
8 | Make sure text fields on Artifact upload form flow to Observation report and end-of-year workbench; Eliminate some of the text fields on the upload page | Release 3 | High | New | Concept
9 | End of year process for purging | Release 2 | High | Leftover | Approved | No longer includes artifacts. The purge date will probably not be until right before Fall (but we'll want to alert teachers before they leave for the summer).
10 | Security process for becoming DA | Release 2 | High | Leftover | Approved | Need by Fall 2015
11 | District Viewer role | Release 2 | High | Leftover | Approved | Need by May (is that possible?)
12 | "Export All" report for teachers | Release 2 | High | Leftover | Approved | Need by mid-May (or find manual solution where we somehow get these reports out to all the teachers before we purge for this year)
13 | Refine online goal setting form and related reports for Seattle | Release 3 | High | Leftover | Approved | Need to analyze; Need ready by Fall 2015
14 | Provide teachers w/ a landing page and a workbench that is centered around the evidence and how that evidence is mapped to the rubric | Release 3 | High | New | Concept | See draft slides for mock-up ideas
15 | Create a year-long evidence collector so that users can add evidence and tie to claim statements outside of a specific observation | Release 3 | High | New | Concept
17 | Remove ability to code at entire domain or criteria level (Excerpt) | Release 3
18 | Change the word "Excerpt" since that word does not exist in TPEP or Danielson methodology | Release 3
19 | District setting to default everything to visible!!!! Then let folks change the setting themselves but across the board | Release 3
20 | New observation dashboard for teachers and evaluators that shows observations in context to the rubric | Release 3 |  |  |  | Slide in progress but needs more thought
21 | Add new dashboard for DA and ED | Release 2 | High |  | Leftover